## Gantt Chart
CMPE 202 - Underwater Softball Sprint Task Sheet
PROJECT TITLE |  | GO - The Final Frontier
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE |  | Act. DURATION | PCT OF TASK COMPLETE | PHASE ONE
[5 empty] | Est. DURATION |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3
[8 empty] | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su
1 | Research and Starter code | Pallavi | 2019-11-04 | 2019-11-07 | 4 | 4 | 100% | bar: WEEK 1 M to WEEK 1 R
2 | User Story Video | Yash | 2019-11-10 | 2019-11-15 | 6 | 4 | 100% | bar: WEEK 1 Su to WEEK 2 Su
3 | Model Design : GoPoint, BoardState, notify View | Gabriel | 2019-11-10 | 2019-11-13 | 4 | 5 | 100% | bar: WEEK 1 Su to WEEK 2 Su
4 | UI: Welcome Screen | Ward | 2019-11-10 | 2019-11-12 | 3 | 4 | 100% | bar: WEEK 1 Su to WEEK 2 Su
5 | Model Design : Interface for Model - UI "Adapter" | Parvathy, Gabriel | 2019-11-11 | 2019-11-13 | 3 | 2 | 100%
6 | UI/Model: UI - Model "Adapter" | Pallavi, Yash | 2019-11-13 | 2019-11-16 | 4 | 6 | 100%
7 | UI: Stone drawing and erasing | ward | 2019-11-13 | 2019-11-15 | 3 | 4 | 100%
8 | Model: Game Logic - Capture Logic | Parvathy | 2019-11-14 | 2019-11-18 | 5 | 7 | 100% | bar: WEEK 2 M to WEEK 3 M
9 | UI Design : Interface for UI - Model "Adapter" | Ward, Pallavi | 2019-11-14 | 2019-11-17 | 4 | 4 | 100% | bar: WEEK 2 M to WEEK 3 W
10 | Model: Game Logic - Capture Logic - Points in "KO" | Parvathy | 2019-11-18 | 2019-11-22 | 5 | 4 | 100% | bar: WEEK 2 M to WEEK 3 F
11 | UI / Model: Refactor for Config Start | Ward | 2019-11-20 | 2019-11-22 | 3 | 2 | 100% | bar: WEEK 3 W to WEEK 3 F
12 | Model: Game Logic - Undo | Gabriel | 2019-11-21 | 2019-11-22 | 2 | 3 | 100% | bar: WEEK 3 R to WEEK 3 F